## HCC Workplan
2018-2019 Central Maine Healthcare Coalition Project Management Plan
Date: | 2019-02-26
# | Task /Subtask Description | Work Output | Due Date | Primary Staff | Secondary Staff | Status | Actual Completion | Notes and Requirements
QUARTER THREE JANUARY 1, 2019 – MARCH 31, 2019
| Capability 4: Objective 2: Activity 1: Collaborate with the Emergency Medical Services for Children (EMSC) program to better meet the needs of children receiving emergency medical care. | Sign-In Sheets or Email Copy | 2019-01-31 |  |  | In Progress
| Coalition Meeting | Meeting Agenda Meeting Minutes Reminder Invite Sent Out | 2019-02-19 |  |  | Completed
| Capability 3: Objective 1: Activity 4: Develop a coalition activity report to share information regarding coalition response planning, training, and exercises with Public Health District Liaisons as well as District Coordinating Councils. | Activity Report | 2019-03-30 |  |  | In Progress
| Capability 1: Objective 1: Activity 1: develop and implement a standardized HCC governance document that is approved by 100% of the coalition’s members. | HCC Governance Document/By Laws | 2019-03-31 |  |  | Not Started
| Capability 1: Objective 2: Activity 3: Obtain de-identified data from the U.S. Department of Health and Human Services emPOWER map every six months to identify populations with unique health care needs. | Deidentified emPOWER data set | 2019-03-31 |  |  | Completed
| Capability 2: Objective 1: Activity 3: Develop and disseminate a situation report of to its members’ health care executives, clinicians, and community leaders in debriefs related to exercises, planned events, and real incidents. | Situation Report | 2019-03-31 |  |  | In Progress |  | Will need to develop a ListServ for coalition stakeholders
| Capability 2: Objective 1: Activity 9: Define and share essential elements of information (EEIs) with its members as well as the Department. | Defined list of EEIs | 2019-03-31 |  |  | Not Started
| Capability 2: Objective 1: Activity 11: Develop and implement a regional health care coalition response plan that has been approved by 100% of the coalition’s members. | Response Plan | 2019-03-31 |  |  | In Progress
| Quarterly Progress Report | Progress Report Submission | 2019-04-15 |  |  | Not Started |  | Highlight the work plan activities during the previous month. Each report will be prepared and submitted using Microsoft Excel to include: • Deliverable status update with supporting documentation • Governance document(s) status with supporting documentation • HVA results with supporting documentation • Regional health care resources assessment results with supporting documentation • Progress y coalition member regarding national provider identification (NPI) number and their compliance with the 11 NIMS implementation activities. • Annual Healthcare Coalition Assessment results (into HCCAT) • Multi-year training and exercise proposal • Annual inventory report of equipment and supplies • Coalition surge test results are submitted to the HCCAT Submit to Program Administrator
QUARTER FOUR APRIL 1, 2019 – JUNE 30, 2019
| Coalition Meeting | Meeting Agenda Meeting Minutes Reminder Invite Sent Out | 2019-04-30 |  |  | Not Started
| Capability 1: Objective 2: Activity 3: Obtain de-identified data from the U.S. Department of Health and Human Services emPOWER map every six months to identify populations with unique health care needs. | Deidentified emPOWER data set | 2019-06-30 |  |  | Not Started
| Capability 1: Objective 2: Activity 1: complete a coalition-based hazard vulnerability analysis (HVA), in collaboration with the Department. | Coalition HVA | 2019-04-30 |  |  | Not Started
| Capability 1: Objective 2: Activity 2: complete a regional health care resources and services assessment to identify regional health care resources and services that are vital for continuity of health care delivery during and after an emergency, and share the report’s results to all 100% of the coalition’s members | Resources and Services assessment | 2019-05-30 |  |  | Not Started
| Capability 2: Objective 1: Activity 1: promote completion of role-Appropriate NIMS training opportunities for 100% of coalition members. | Email/Potential NIMS Course | 2019-04-30 |  |  | Not Started
| Capability 3: Objective 1: Activity 1: Facilitate the completion of three bed availability drills with 75 of the coalition’s members reporting the data to the Department within four hours of notification. | • Completed Bed Availability Drill • List of Coalition Partner Participation • Data Collection | 2019-06-30 |  |  | Not Started
| Capability 3: Objective 1: Activity 2: Document the coalition’s information sharing procedures in the HCC’s response plan. | Information Sharing Procedures | 2019-03-30 |  |  | Not Started
| Capability 4: Objective 1: Activity 3: Complete an annual Coalition Surge Test (CST) in each coalition region. | • Completed ASPR CST Tools • Debrief Sign-in Sheets | 2019-06-30 |  |  | Not Started
| Quarterly Progress Report | Progress Report Submission | 2019-07-15 |  |  | Not Started |  | Highlight the work plan activities during the previous month. Each report will be prepared and submitted using Microsoft Excel to include: • Deliverable status update with supporting documentation • Governance document(s) status with supporting documentation • HVA results with supporting documentation • Regional health care resources assessment results with supporting documentation • Progress y coalition member regarding national provider identification (NPI) number and their compliance with the 11 NIMS implementation activities. • Annual Healthcare Coalition Assessment results (into HCCAT) • Multi-year training and exercise proposal • Annual inventory report of equipment and supplies • Coalition surge test results are submitted to the HCCAT Submit to Program Administrator

## List
Not Started
In Progress
Completed

## Settings (hidden)
SWCHCC Settings
Status
In Progress
Complete
Not Started